## PMR
Department of Migrant Workers - Caraga Regional Office | [9 empty] | Procurement Monitoring Report as of December 31, 2025
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES | [14 empty] | 0
5020311000 | Supply and delivery of office supplies for the 4th quarter of CY 2025 | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-03-10 | 2025-10-24 | 2025-10-24 | 28-10-2025 | 28-10-2025 | Regular | 252105 | 252105 |  | 246809 | 246809 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020311000 | Supply and delivery of additional carious supplies for the 4th quarter of CY 2025 | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-12-12 | 2025-12-12 | Regular | 116115 | 116115 |  | 116088 | 116088 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Tarpaulin during the session on the Capacity Buildging program for Children of OFWs at PNU Mindanao campus, every Wednesday of the month | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 2025-08-09 | 16-9-2025 | 16-9-2025 | 16-9-2025 | 16-9-2025 | Regular | 1000 | 1000 |  | 600 | 600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Supplies during the session on the Capacity Buildging program for Children of OFWs at PNU Mindanao campus, every Wednesday of the month | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 2025-08-09 | 16-9-2025 | 16-9-2025 | 16-9-2025 | 16-9-2025 | Regular | 44190 | 44190 |  | 15805 | 15805 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020321000 | Procurement of additional printers for DMW Caraga 2025 | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 29/9/2025 | 29/9/2025 | 16-10-2025 | 16-10-2025 | 27-10-2025 | 27-10-2025 | Regular | 171500 | 171500 |  | 139986 | 139986 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020321000 | Procurement of scanners for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 2025-08-09 | 30-10-2025 | 30-10-2025 | 2025-03-11 | 2025-03-11 | Regular | 230000 | 230000 |  | 225540 | 225540 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Tarpaulin during the celebration of the 36th National Statistics Month | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-9-2025 | 26-9-2025 | 26-9-2025 | 26-9-2025 | 26-9-2025 | 26-9-2025 | Regular | 640 | 640 |  | 480 | 480 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals during the celebration of the 36th National Statistics Month | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-9-2025 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 27-10-2025 | 27-10-2025 | Regular | 11500 | 11500 |  | 11500 | 11500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals during the conduct of Financial Awareness Seminar and Small Business Management Training (FAS-SBMT) on Sept. 29, 2025 | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-9-2025 | 26-9-2025 | 26-9-2025 | 26-9-2025 | 29-9-2025 | 29-9-2025 | Regular | 28500 | 28500 |  | 28500 | 28500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals during the DMW Staff in celebration of Kainang Pamilya Mahalaga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18-9-2025 | 18-9-2025 | 19-9-2025 | 19-9-2025 | 22-9-2025 | 22-9-2025 | Regular | 12000 | 12000 |  | 12000 | 12000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Materials during the conduct of capacity building of Protection Services Staff Cum Alternative Dispute Resolution / Single Entry Approach (SENA) on Sept. 12, 2025 | MWPTD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-12-09 | 2025-12-09 | Regular | 2195 | 2195 |  | 1450 | 1450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Tokens during the conduct of capacity building of Protection Services Staff Cum Alternative Dispute Resolution / Single Entry Approach (SENA) on Sept. 12, 2025 | MWPTD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-12-09 | 2025-12-09 | Regular | 1990 | 1990 |  | 1990 | 1990 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals during the 125th Philippine Civil Service Anniversary | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 17-9-2025 | 17-9-2025 | Regular | 8500 | 8500 |  | 8500 | 8500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5060405003 | Procurement of ICT Equipment for DMW Caraga Regional Office CY 2025 | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14-10-2025 | 31-10-2025 | 19-11-2025 | 19-11-2025 | 2025-01-12 | 2025-01-12 | Regular | 1935000 |  | 1935000 | 1564200 |  | 1564200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Supplies and materials during the celebration of the 4th DMW Anniversary | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-10 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 15-12-2025 | 15-12-2025 | Regular | 10000 | 10000 |  | 10000 | 10000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals: Orientation and Presentation of Proposed Collaborative Initiatives between the Department of Migrant Workers Regional Office RO XIII and Father Saturnino Urios University on December 17, 2025 at the Office of the President, Board room, San Francisco St., Butuan City | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-12 | 15-10-2025 | 15-10-2025 | 15-10-2025 | 17-12-2025 | 17-12-2025 | Regular | 5000 | 5000 |  | 5000 | 5000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Token for the DMW Best Dressed Award. | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-10-12 | 2025-10-12 | Regular | 3000 | 3000 |  | 3000 | 3000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | For DMW ROXIII during the conduct of "Financial Awareness Seminar and Small Business Management Training (FAS-SBMT) on December 4, 2025 | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-12 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-04-12 | 2025-04-12 | Regular | 39600 | 39600 |  | 39600 | 39600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Supplies and Materials for DMW Year- End Performance Assessment and 2026 Planning Exercise. | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-11-2025 | 2025-01-12 | 2025-01-12 | 2025-01-12 | 2025-09-12 | 2025-09-12 | Regular | 10000 | 10000 |  | 10000 | 10000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Meals and Pica-pica during the conduct of DMW 2025 Year-End Assessment and 2026 Planning Exercise | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-11-2025 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-12-12 | 2025-12-12 | Regular | 42250 | 42250 |  | 42250 | 42250 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Tarpaulin for DMW 4th Anniversary | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 18-12-2025 | 18-12-2025 | Regular | 1000 | 1000 |  | 990 | 990 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Tarpaulin for DMW 2025 Year-End Performance Assessment and 2026 Planning Exercise | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-12 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-08-12 | 2025-08-12 | Regular | 1000 | 1000 |  | 990 | 900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020321000 | To support office operations by providing backup power for the all-in-one PC (UPS), enabling wireless presentations (Wireless HDMI), and improving audio connectivity (Bluetooth Receiver). | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-12 | 2025-11-10 | 2025-10-12 | 2025-10-12 | 2025-12-10 | 2025-12-10 | Regular | 138300 | 138300 |  | 138068 | 138068 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Procure customized Desk Calendar and go bags for stakeholders/partner agencies and corporate jacket for DMW staff to be distributed during the 4th DMW Anniversary. | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-12 | 15-12-2025 | 15-12-2025 | 15-12-2025 | 18-12-2025 | 18-12-2025 | Regular | 208180 | 208180 |  | 208180 | 208180 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Christmas decorations for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21-11-2025 | 24-11-2025 | 24-11-2025 | 24-11-2025 | 29-11-2025 | 29-11-2025 | Regular | 71900 | 71900 |  | 71805 | 71805 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Meals during the celebration of the 4th DMW Anniversary | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-11 | 21-11-2025 | 21-11-2025 | 21-11-2025 | 25-12-2025 | 25-12-2025 | Regular | 70000 | 70000 |  | 70000 | 70000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Advocacy shirt in celebration of the 18-Day Campaign to End violence Against Women | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17-11-2025 | 17-11-2025 | 17-11-2025 | 17-11-2025 | 25-11-2025 | 25-11-2025 | Regular | 30550 | 30550 |  | 23500 | 23500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | To procure roll-up banner to promote programs and services of DMW RO XIII | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 18-12-2025 | 18-12-2025 | Regular | 1500 | 1500 |  | 1320 | 1320 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | To procure roll-up banner to promote programs and services of DMW RO XIII | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 18-12-2025 | 18-12-2025 | Regular | 10000 | 10000 |  | 9000 | 9000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Signages for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-10-11 | 15-12-2025 | 15-12-2025 | 16-12-2025 | 16-12-2025 | Regular | 373600 | 373600 |  | 346084 | 346084 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Token for the Resource Person during the conduct of Safe Space Act Orientation in celebration of the 18-Day Campaign to End violence Against Women | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-11 | 17-11-2025 | 17-11-2025 | 17-11-2025 | 25-11-2025 | 25-11-2025 | Regular | 1500 | 1500 |  | 1500 | 1500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020322000 | Procurement of furniture and fixture for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-11 | 14-11-2025 | 14-11-2025 | 14-11-2025 | 21-11-2025 | 21-11-2025 | Regular | 401000 | 401000 |  | 394000 | 394000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Snacks during the conduct of Project Bahandi: Selected IP Community activity in Surigao del Sur | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-12-11 | 2025-12-11 | Regular | 12500 | 12500 |  | 12500 | 12500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Snacks during the Orientation on Safe Space Act in support to the 18-Day Campaign to End Violence Against Women | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 25-11-2025 | 25-11-2025 | Regular | 6000 | 6000 |  | 6000 | 6000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Procurement of Emergency Go Bags with Essentials and Vest to strengthen disaster preparedness among DMW RO XIII-Caraga QRT Members | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 23-12-2025 | 23-12-2025 | Regular | 180000 | 180000 |  | 152500 | 152500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5029903000 | Meals and venue during the conduct of "Caraga Region Reintegration Network (CarRReN) Institutional Meeting on October 17, 2025" | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14-10-2025 | 16-10-2025 | 16-10-2025 | 16-10-2025 | 17-10-2025 | 17-10-2025 | Regular | 30000 | 30000 |  | 30000 | 30000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Presentation, information, and annoucement dissimination for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28-9-2025 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 21-11-2025 | 21-11-2025 | Regular | 65000 |  | 65000 | 65000 |  | 65000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5060405002 | Speakers and mixer for DMW Caraga Conference Room | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 21-11-2025 | 21-11-2025 | 21-11-2025 | 26-11-2025 | 26-11-2025 | Regular | 210000 |  | 210000 | 205000 |  | 205000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Documentation purposes for all the activities of DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 24-11-2025 | 28-11-2025 | 28-11-2025 | 28-11-2025 | 2025-09-12 | 2025-09-12 | Regular | 150000 |  | 150000 | 150000 |  | 150000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50604050002 | Outside activities of DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 2025-02-10 | 2025-04-12 | 2025-04-12 | 16-12-2025 | 16-12-2025 | Regular | 65000 |  | 65000 | 64998 |  | 64998 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5021304001 | Procurement of frosted sticker and customized rostrum for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 16-12-2025 | 16-12-2025 | Regular | 224990 | 224990 |  | 210000 | 210000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5020399000 | Tokens during the Pre-Migration Orientation Seminar and Financial Planning - Training of Tranors on September 23-26, 2025 move to Oct. 27-30, 2025 | WRSD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17-10-2025 | 20-10-2025 | 20-10-2025 | 20-10-2025 | 24-10-2025 | 24-10-2025 | Regular | 43250 | 43250 |  | 40775 | 40775 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5060405002 | Procurement of photocopier for DMW Caraga | FAD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 31-10-2025 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 14-11-2025 | 14-11-2025 | Regular | 390000 |  | 390000 | 302331 |  | 302331 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[18 empty] | Total Allotted Budget of Procurement Activities | 5610355 | 2795355 | 2815000
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 4987839 | 2636220 | 2351529
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 622516
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
5060405002 | Procurement of interactive TV for the DMW Conference Room | FAD | No | Small Value Procurement | [7 empty] | 22-12-2025 | 23-12-2025 | 23-12-2025 | 23-12-2025 |  |  | Regular | 480500 |  | 480500 | 480000 |  | 480000
5060405002 | Procurement of television for ARTA and other relevant materials to be digitalized | FAD | No | Small Value Procurement | [7 empty] | 2025-08-09 | 2025-02-10 | 2025-02-10 | 2025-02-10 |  |  | Regular | 260000 |  | 260000 | 259994 |  | 259994
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 740500 | 0 | 740500 | 739994 | 0 | 739994
|  | Prepared by: | [7 empty] | Recommended for Approval by: | [11 empty] | APPROVED:
|  | GIOVANNI S. PAREDES | [7 empty] | REGIENALD S. ESPALDON | [11 empty] | RITCHEL M. BUTAO
|  | BAC Secretariat | [7 empty] | BAC Chairperson | [11 empty] | Head of the Procuring Entity
Formulas:
Notice to Proceed = +Completed[[#This Row],[Contract Signing]]
Notice to Proceed = +Ongoing[[#This Row],[Contract Signing]]
Contract Signing = +Completed[[#This Row],[Notice of Award]]
Contract Signing = +Ongoing[[#This Row],[Notice of Award]]
Inspection & Acceptance = +Completed[[#This Row],[Delivery/ Completion]]
Notice of Award = +Completed[[#This Row],[Date of BAC Resolution Recommending Award]]
Notice of Award = +Completed[[#This Row],[Contract Signing]]

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>